## Sprint 3
TASK |  | Description | Assignee | Estimation (Days) | Attachments | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-08 | 2018-06-11
Requirement Details |  |  |  |  | Detail Document | 2018-06-11: DEADLINE
1. Tax Jar |  | While we are still addressing Sales Tax, we want to implement a 3rd party API in order to ensure we are accurately calculating sales taxes collected. We will be using TaxJar: | Chattan | 6 | TaxJar | bar: 2018-05-23 to 2018-05-30
|  | TaxJar uses the customers address to calculate the correct sales tax. including any local, county or city taxes, which we currently aren't doing. This should be pretty easy for us to add to our system, we just send an API request at checkout, instead of calculating the sales tax ourselves. |  |  | developers.taxjar.com
|  | For each order, when an order is being placed in the cart, and the customer has entered/selected their address, submit a request for the tax amount: |  |  | Api Reference
|  | Only orders where the shipping address is in Florida, and where the client/customer is not Tax Exempt. need to be submitted. I think the only fields in the result we need are: "amount_to_collect" & "rate" and possibly "taxable_amount" for verification. This should also be used to calculate sales tax for order being placed from the admin. We also want to display the tax rate to the customer, if there is no sales tax display sales tax as 0.0 %. |  |  | Image
We will need to add a tax_rate field to the transactions table, and a tax rate column to the orders list in the Reports / Sales Tax page.
1.1 Tax Jar Addon Tasks from previous timeline |  | 1. Sales Tax PDF When we add tax rate to other pages, we should also include it here. | Chattan | 2 | bar: 2018-05-30 to 2018-05-31
2. Coupon Invoice PDF The sales tax should be it's own column. Also, don't forget to add the tax rate to this page, when adding tax rate to other pages.(After Tax jar implemented)
2. Product Importing |  | We currently import all product data from our vendor data into our products data table, but with an inactive status, then enable the product from the Product Import page. | Sanjay | 7 | bar: 2018-05-08 to 2018-05-16
1. Change this so that when we copy the vendor product data, for products we don't have, these products are saved in a json file instead of being added to the database.
2. Then, when we go to the Product Import page, this json file is used to generate the product import list. And add the product to the database when the product is Imported.
3. We should also make sure that each item is only in our database once, And is not available to be imported if the items UPC, SKU, etc. exists.
4. And, since we don't want this extra product data that is not in use, remove all of the product data of inactive products currently in our database.
3. Product Data Updating |  | 1. Instead of updating the product data automatically we need to add an approval process to verify that the update won't break the product. This approval should just be a list of changes that we can click a button to approve or ignore. When we click the button to approve the change, our product data is updated. | Sanjay | 7 | bar: 2018-05-15 to 2018-05-23
2. We can also slow down our requests for the product data from our vendors. The product data shouldn't change very often, so we should only be updating our copy of the vendor data once a month. ( But we will still be updating the inventory data daily. )
3. With this in place, we should be able to quickly click through a list of changes once a month, and be able to avoid any changes that we don't want. Most changes we want to be able to account for: • Price • Title • Status (Discontinued, etc.) • New Color • Discontinued Color Here is a first draft design, let me know if you have any suggestions : Refer Yurstore-Requirement Verification Document
4. Product Status |  | 1. After we've removed all of the inactive products, let's use the status column. Add a button to each product to change the status of the product. Inactive products should still be listed in the admin, but not displayed in stores.
5. Vendor API/FTP |  | 1. Let's make sure that vendor API's are using the credentials in the API/FTP tabs of the Vendor Info pages. and not hard coded into the API's. So that if this info is changed we can quickly update this info. If needed, update the API/FTP Info tab forms to ensure that ALL of the info required is included. | Chattan | 3 | bar: 2018-05-08 to 2018-05-10
2. Separate this API info section into multiple tabs, each tab according to the function of the API. • Inventory • Product Data • Order Submission ( future project) • Invoice Tracking ( future project )
3. Make sure we can disable/enable each API for any vendor just in case there is an error with the API.
6. Vendor Ordering |  | We would like to submit orders directly to our vendors: • sending the order via email to a preset email address • using their api/ftp options ( future project ). | POSTPONED BY CLIENT | TBD
1. Add an Order Submission Email field to the Vendor Details form.
2. On Vendor-Order page, after the items have been selected, add a "Send Order" button to the order submission modal if the vendor has an email to send the order to. When "Send Order" is clicked, send an email to the address on file, including the PO number and the item list table.
3. And we need a printable list of the items ordered. Also, add a select all button to select all items that need to be ordered
7. Item Cost Field |  | 1. In order to improve the accuracy of our pricing, and to correct the issue we're having with products with one discontinued color. Add a "cost" column to the "product_color_size" database table, (this may have already been done) When this price is imported from the vendor data. Use this price when calculating prices. Only use cost field in the products table if this value is missing. Remove the additional pricing on the extra large sizes. The extra pricing is no longer needed. | Sanjay | 5 | bar: 2018-05-22 to 2018-05-28
8. Product Colors |  | 1. To correct AlphaBroder misspelled colors and numbers, copy the current "color_name" into the "color_code" field. Use the "color_code" field to match items in the vendor data instead of "color_name" Remove numbers and special characters from the Color Names Make sure that we can change the Color Name, without breaking the association between the vendor data and our data. (Since "color_code" will be used) We will also want to do this for SanMar, but they have fewer spelling errors. | Sanjay | 4 | bar: 2018-05-24 to 2018-05-29
//My final understanding 1. Copying data of 'color_name' to 'color_code' in 'colors' table by overwriting previous 'color_code' value from 'colors' table; 2. During product import comparing vendor product 'color_name' with 'color_code' in 'colors' table; (note: not using vendor 'color_code' since some vendor products with 'color name' like 'white/black/grey' has only one color code and our 'colors' table contains 'color_name' like 'white', 'black', 'grey' but not 'white/black/grey' 3. removing number and special character from 'color_name' in 'colors' table;
9. Product Images |  | 1. Instead of requiring that our product image names be formatted in a particular way, let's just change the image name to the format we want when we save the image. Let's add a small drag/drop area to each color name. When an image is dropped onto this area the image should be renamed and saved. | POSTPONED BY CLIENT | TBD | Image
2. We should also add a button to import the images from the vendor data, which should only be available when any/all product images are missing, and those images exist in the vendor data.
10. More Product Images |  | 1. Add the ability to add images of the product from more angles The current images are all "front" images. We need to add "left", "right", "back", "top" and "bottom" These images should be displayed as a grid in the admin:
2. Ideally, we should be able to drag and drop an image into a cell, to automatically rename and upload a photo. We also need to be able to add images with no color.
11. Product Lengths |  | Products with different lengths available are not being displayed correctly. The Petite, and Tall lengths are displayed as options to select, but the default length "Regular" is not available. | Sanjay | 6 | bar: 2018-05-29 to 2018-06-05
1. We need to add the Regular length to the product in the database, so that the product details page recognizes that as a selectable length. | bar: 2018-05-08 to 2018-05-28; 2018-06-06 to 2018-06-11
2. Just like the behavior of sizes. No length is preselected, but when the customer selects a length, that length should be remembered is preselected during that session. | bar: 2018-05-08 to 2018-05-28; 2018-06-06 to 2018-06-11
Index
Chattan
Sanjay
Testing and Debugging
Verified in QA Deployment
Postponed / Days passed